## Sheet1
FY 2018 LCoC NOFA |  |  |  | 08.16.18
Item | Date - Dates in bold are required by the NOFA | Who Responsible | Done | Comments
CoC Registration | Opened April 30, due May 14, Review May 24, 2018 | Karen Byron | X
NOFA Release | 06.20.18 | HUD | X
Review NOFA-relevant webinars as they become available | TBD | Interested parties | X | Karen will notify CoC of dates and times as webinars become available, and will provide links to registration if possible.
Applications available in e-snaps; instructions available in HUD Exchange | 07.02.18 | HUD | X
RFP Issued for New, Reallocated, Bonus funds and DV Bonus funds | 07.16.18 | Olivia, Karen | X
Meetings with Renewal applicants to review project data | Week of 07.16.18 | KRB and projects | X
Develop Ranking and Review Tool, and send to CoC for comment. | 07.18.18 | KRB | X
Meeting to review NOFA changes from previous years, what is new, CoC-required tasks, discuss reallocations proposed (if any), and the Ranking and Review Tool as well as requirements for new projects. | 07.23.18 | Interested parties | X | 11:00-1:00, 10 Church Street Community Room
New project concept papers due | 07.24.18 | Applicants | X
Transition grant description to the LCoC per RFP Instructions | 07.24.18 | Applicants | X
Review of Consolidated Application line-by-line | 08.01.18 | All interested parties | X | Please note this will potentially be a 2-3 hour meeting. Participants should review the blank Consolidated Application Karen will send out prior to meeting. 9:00-12:00, 10 Church Street, Community Room
New and Renewal Applicants present their projects to the Ranking and Review Committee | 08.06.18 | All parties submitting requests | X | Please note: Applicants wishing to consolidate must first consult Samantha Graves, p. 9 of NOFA; meeting is 9:00-11:00, 10 Church Street, Community Room
Ranking and Review Committee meet to accept or reject new proposals | 08.06.18 | KRB and Committee | X
First draft of applications and attachments in esnaps | 08.19.18 | KRB and Applicants | X
All Applications received by CoC in esnaps | 08.20.18 | KRB
Comments regarding applications to KRB | 08.21.18 | Ranking and Review Committee, KRB
Draft of Consolidated Application Section 1 | 08.21.18 | KRB
Comments on Consolidated Application Section 1 | 08.23.18 | LCoC Membership
Draft of Consolidated Application section 2 | 08.23.18 | KRB
Final project applications and all attachments due in esnaps | 08.24.18 | KRB and Applicants
Comments on Consolidated Application Section 2 | 08.27.18 | LCoC membership
Ranking and Review Committee meets to determine final ranking | 08.28.18 | Ranking and Review Committee, KRB
Ranking and Review Decisions presented to CoC electronically for approval | 08.28.18 | Olivia; Ranking and Review Committee; Karen
Draft of Consolidated Application section 3 | 08.28.18 | KRB
Comments on Consolidated Application Section 3 | 08.30.18 | LCoC membership
Draft of Consolidated Application section 4 | 08.30.18 | KRB
Comments on Consolidated Application Section 4 | 09.03.18, noon | LCoC membership
Final draft of Consolidated Application for review | 09.04.18 | KRB
All applications acepted or rejected by CoC | 09.04.18 | LCoC membership
Notification of acceptance, rejection or reduction of project applications in the Priority Listing in writing | 09.04.18 | Karen Byron
Final comments on Consolidated Application | 09.05.18 | LCoC membership
Full NOFA response available on LHAND website and partner websites for public review | 09.05.18 | LHAND and KRB
Electronic vote to accept or reject the Consolidated Application, Priority Listing and Project Applications | 09.12.18 | LCoC membership
Final Consolidated Application, Priority Listings and Project Applications with additional comments from public | 09.14.18 | Karen Byron
NOFA submitted | 09.14.18 | Karen Byron
NOFA responses due | 09.18.18
Complete
In progress